## Sheet1
Sort by priority | Description of risk | Owner | Possible impact | Prob (%) | Impact (L, M, H, VH) | Risk code (color per table) | Mitigation plan
1 | Unauthorized system access risk | System Administrator | Compromise system security and data breach | 1% | VH | Yellow | Enforce strong password policies, Implement MFA
2 | Data inconsistency risk | Inventory Manager | Errors in product information leading to reporting issues | 30% | M | Yellow | Use input validation, Provide staff training
3 | Budget miscalculation risk | Administrator | Inaccurate financial planning and overspending | 30% | M | Yellow | Automate calculations, Test and validate budget formulas
4 | System downtime risk | System Administrator | Operational disruption and data loss | 1% | VH | Yellow | Use a reliable hosting service
5 | Unregistered purchase risk | Inventory Manager | Missed transactions and inventory mismanagement | 30% | M | Yellow | Provide user training, Show system notifications
6 | Unauthorized budget adjustments risk | Administrator | Loss of financial control and potential fraud | 20% | H | Yellow | Apply role-based access control, Implement approval workflow
7 | Omission in shopping list risk | Inventory Manager | Stock shortages and order inaccuracies | 30% | L | Green | Train staff to follow process, Validate item addition steps