## Sheet1
Sort by priority | Description of risk | Owner | Possible impact | Prob (%) | Impact (L, M, H, VH) | Risk code (color per table above) | Mitigation plan
1 | Unauthorized access | Project Team | Access to private medical data, breach of privacy | 10% | VH | Yellow | Enforce strong password policies, store login info securely
2 | Inaccurate test data entry | Nurse | Wrong medical follow-up decisions | 10% | VH | Yellow | Provide short data entry training, add basic input checks
3 | Missing follow-up list updates | Nurse | Veterans not receiving timely follow-up | 30% | H | Yellow | Send daily reminder, keep a simple check-list
4 | Outdated daily medicine list | Nurse | Wrong medication given | 20% | VH | Yellow | Cross-check with official prescription sheet once a day
5 | Lost or incomplete veteran details | Project Team | Data confusion, repeated registration steps | 10% | H | Green | Keep a simple backup of the data file, store minimal info in a separate place
6 | System downtime | Project Team | Nurse cannot access or update data | 5% | H | Green | Use stable hosting environment, keep a local copy of the app
7 | Confusion between system modules | Project Team | Nurse mistakes or duplication of data | 20% | H | Green | Provide simple user instructions, keep the UI consistent